## Listing
ID | Descriptive | Requirement | Rating | Req Rating | Allocated Too | Finished | Peer Review By | Signed off By | Status
1 | Customer Discount | Could Have | 2 | Could Have 2 |  |  |  |  | Unallocated
2 | Search by keyword or job code | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
3 | Linkedin | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
4 | Pinteret | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
5 | Twitter | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
6 | Facebook | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
7 | Search by the warehouse group business | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
8 | search results to seperate pages | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
9 | Front end Log in features | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
10 | Search by Expertise | Could Have | 3 | [5 empty] | Unallocated
11 | Search by Employment Type | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
12 | Search by experience level | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
13 | Product Page quantity Select | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
14 | Products Page add to cart button | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
15 | Product Page facebook like button | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
16 | Product Page add to wishlist button | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
17 | Product Page print this page button | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
18 | Product Page email to a friend button | Won't Have | 6 | Won't Have 6 |  |  |  |  | Not to be done
19 | Product Page pinterest button | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
20 | Product Page "People who viewed this item also viewed" display | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
21 | Product Page which category it is in | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
22 | Product description | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
23 | Apply now Button (Job) | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
24 | Email to a friend button (Job) | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
25 | Print button (Job) | Could Have | 5 | Could Have 5 |  |  |  |  | Unallocated
26 | Virtual Store | Won't Have |  | Won't Have |  |  |  |  | Not to be done
27 | Virtual Support Office | Won't Have |  | Won't Have |  |  |  |  | Not to be done
28 | Virtual distribution centre | Won't Have |  | Won't Have |  |  |  |  | Not to be done
29 | Clickable staff members, bios staff information | Could Have | 6 | Could Have 6 |  |  |  |  | Unallocated
30 | refreshing cart page after editing | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
31 | Form to register for access to webcast | Won't Have |  | Won't Have |  |  |  |  | Not to be done
32 | Login Form ( User or Admin) | Must Have | 1 | Must Have 1 | BD |  |  |  | Allocated
33 | Forgot password reference | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
34 | Register form | Must Have | 1 | Must Have 1 | BD |  |  |  | Allocated
35 | Registration button | Must Have | 1 | Must Have 1 | BD |  |  |  | Allocated
36 | Order form | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
37 | Track order functionality | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
38 | Find tracking number | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
39 | Create a shopping cart | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
40 | Delivery radio button from cart | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
41 | Pick up radio button from cart | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
42 | Change product quantity from cart | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
43 | Remove product from cart | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
44 | Discount Code application field | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
45 | Item star ratings | Should Have | 4 | Should Have 4 |  |  |  |  | Unallocated
46 | Item comment/review field | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
47 | Item testimony | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
48 | Donation radio button, shopping cart | Won't Have |  | Won't Have |  |  |  |  | Not to be done
49 | Item wishlist (Not bought but favorited) | Should Have | 4 | Should Have 4 |  |  |  |  | Unallocated
50 | Price and delivery calculations | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
51 | Currency converter | Won't Have |  | Won't Have |  |  |  |  | Not to be done
52 | Continue shopping button from cart | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
53 | Go to checkout button (Take to payment screen) | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
54 | Refund functionality | Could Have | 5 | Could Have 5 |  |  |  |  | Unallocated
55 | Cancel orders | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
56 | Search store functionality | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
57 | Google maps locations | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
58 | Find a store function | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
59 | Public certification of website | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
60 | PDF item catalog - link to DB | Should Have | 4 | Should Have 4 |  |  |  |  | Unallocated
61 | Warehouse master card registration form | Won't Have |  | Won't Have |  |  |  |  | Not to be done
62 | Travel insurance form/qoute | Won't Have |  | Won't Have |  |  |  |  | Not to be done
63 | Mutiple languages | Won't Have |  | Won't Have |  |  |  |  | Not to be done
64 | Search by keyword | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
65 | Search filter by catagory | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
66 | Search filter by subcategory | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
67 | Search filter by brand | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
68 | Search filter by clearance stock | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
69 | Search filter by genre | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
70 | Search filter by item promotions | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
71 | Search filter by price range | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
72 | Product View in grid | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
73 | Product View as a list | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
74 | Sorting functions | Should Have | 1 | Should Have 1 |  |  |  |  | Unallocated
75 | Sort by popularity | Should Have | 1 | Should Have 1 |  |  |  |  | Unallocated
76 | Sort by the lowest price | Should Have | 1 | Should Have 1 |  |  |  |  | Unallocated
77 | Sort by the highest price | Should Have | 1 | Should Have 1 |  |  |  |  | Unallocated
78 | Sort by name / alphabetically | Should Have | 1 | Should Have 1 |  |  |  |  | Unallocated
79 | Product List Page select | Should Have | 2 | Should Have 2 |  |  |  |  | Unallocated
80 | Releated searchs displayed | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
81 | Previously viewed items displayed | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
82 | HTML media queries | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
83 | Tablet combatability | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
84 | Smartphone combatability | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
85 | Desktop/laptop combatability | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
86 | Orientation change landscape/portrait | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
87 | Data-based Encryption/Hashing | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
88 | Public Key Certificate | Should Have | 4 | Should Have 4 |  |  |  |  | Unallocated
89 | Templates for website php can fill them | Must Have | 1 | Must Have 1 |  |  |  |  | Unallocated
90 | URL verification (https://) | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
91 | Error Identification | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
92 | Text-based alternatives | Should Have | 3 | Should Have 3 |  |  |  |  | Unallocated
93 | Search Engine Optimization (SEO) | Must Have | 4 | Must Have 4 |  |  |  |  | Unallocated
94 | Anchor tags/Navigability | Won't Have |  | Won't Have |  |  |  |  | Not to be done
95 | Item on hand or in stock | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
96 | Item ETA | Won't Have |  | Won't Have |  |  |  |  | Not to be done
97 | Tax Management | Won't Have |  | Won't Have |  |  |  |  | Not to be done
98 | Time-based media | Won't Have |  | Won't Have |  |  |  |  | Not to be done
99 | Customer Account management (Admin) | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
100 | change email address | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
101 | change home address | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
102 | chage contact details | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
103 | Error Prevention (Reversible Submissions) | Should Have | 5 | Should Have 5 |  |  |  |  | Unallocated
104 | Error Prevention (Input Error Gate) | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
105 | Error Prevention (Confirmation Mechanism) | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
106 | clicking on an item in shopping cart should still link to page | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
107 | XML Sitemap | Must Have | 5 | Must Have 5 |  |  |  |  | Unallocated
108 | robots.txt | Must Have | 5 | Must Have 5 |  |  |  |  | Unallocated
109 | Customer Account management (User) | Must Have | 2 | Must Have 2 |  |  |  |  | Unallocated
110
111
112 | Discount Matrix | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
113 | Invoice PDF Emailing | Could Have | 4 | Could Have 4 |  |  |  |  | Unallocated
114 | Product Backorder | Could Have | 3 | Could Have 3 |  |  |  |  | Unallocated
115 | Repricing of products | Must Have | 3 | Must Have 3 |  |  |  |  | Unallocated
116 | Administration screen to CRUD Products | Must Have | 1 | Must Have 1 | HM |  |  |  | Allocated
117 | Administration screen to CRUD Customers | Must Have | 1 | Must Have 1 | DM |  |  |  | Allocated
118 | Customer Table in Database | Must Have | 1 | Must Have 1 | JE |  |  |  | Allocated
119 | Products Table in Database | Must Have | 1 | Must Have 1 | CM |  |  |  | Allocated
120 | Customer Logon | Must Have | 1 | Must Have 1 | BD |  |  |  | Allocated
121 | Display of products for end users | Must Have | 1 | Must Have 1 | GM |  |  |  | Allocated
122 | Design of Database tables | Must Have | 1 | Must Have 1 | RW |  |  |  | Allocated
123 | Invoice Feature | Must Have | 1 | Must Have 1 | RW |  |  |  | Allocated
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## Control Sheet
Requirement | Ratings | Team Members
Must Have | 1 | BD | Bruce Dolamore
Should Have | 2 | CM | Cainton Milroy
Could Have | 3 | DM | David Mullan
Won't Have | 4 | HM | Hayden McLaren
Unclasified | 5 | JE | Jack Eaton
| 6 | RW | Ross Woodgate
|  | GM | Glen Mcneur